Changing Paradigms in Human Services

Project Structure and Overview of Work Plan

Initial Template

Subject to Revisions and Feedback

July 22, 2004

Changing Paradigms in Human Services

Project Overview – July 2004

The overall goal of this project is to facilitate change in the human service sector of Nashville in order to prevent social and psychological problems, empower community residents to take control of their lives, address roots causes of problems, and improve the conditions that dictate quality of life for people who experience disadvantage. These changes would move the human service sector closer to a transformative paradigm, and further away from a merely ameliorative or reactive paradigm. While many agencies strive to accomplish these goals on their own, and may have had a modicum of success, they have expressed a need for help in furthering these changes and in documenting them.

Therefore, this project entails research and consultation with three distinct groups: (a) Family Resource Centers (FRCs), (b) Lead Agencies housing FRCs, and (c) the United Way of Nashville. The research and consultation will focus on processes and outcomes of change at various levels within each of the three groups of agencies described above:

- Individual workers

- Teams within each agency

- Organization as a whole

Change at these three levels is aimed at promoting change in two further domains:

- Communities

- Policy context

The goal of changing numbers 1 through 3 is to effect improvements not only within the agency, but in communities as well. Table 2 describes the concrete actions that we are likely to pursue, in collaboration, with United Way, FRCs, and their lead agencies. The actions will determine the likely deliverables at each level.

Table 2 describes many actions aimed at fostering a transformative paradigm in human and community services. To make sure we understand what the transformative paradigm is all about, we present in table 1 a synopsis of its main features and contrast it to the dominant ameliorative paradigm. As may be seen in table 1, the transformative paradigm does not invalidate the ameliorative one but rather expands it. In other words, the former does not seek to replace the latter but rather to enhance its scope.

Table 1: Main Features of Ameliorative and Transformative Paradigms

| Features of Human Services | Ameliorative Paradigm | Transformative Paradigm adds…. |
| --- | --- | --- |
| Problem definition | Individual and interpersonal sources | Community sources such as prevalence of violence and poverty |
| Focus of intervention | Individual and family | Systems in the community affecting personal, interpersonal, and collective wellness |
| Timing of intervention | Reactive | Proactive |
| Type of intervention | Expert-driven | Collaborative partnerships |
| Target of intervention | Child, adolescent, parent, family | Schools, government policies, and community conditions |
| Content of intervention | Skill building, self-help, therapy | Advocacy, community empowerment, policy change |
| Role of resident seeking services | Mainly passive recipient of services | Active collaborator in creating community change |
| Desired outcomes | Improved functioning at the personal and family level | Improved access to vital services such as health care, child care, transportation and public education |
| Decision-making processes | Professional driven | Community participation |
| View of human growth | Independence | Interdependence |
| Type of caring | Proximal | Distal |
| Values | Health and growth | Participation and fair distribution of opportunities in society |
| Health promotion | Personal | Public and community |
| Preferred actions | Individual | Collective and systemic |

Table 2: Team’s Actions and Deliverables At Different Levels Of Change Within Agencies And Communities

| Levels of Change (within Agencies – United Way/FRCsLead Agencies – and Communities) | Consultation for Change | Research on Change |
| --- | --- | --- |
|  | Process (How we Intervene) | Outcomes (What we Hope to Achieve) | Process (Study How Questions) | Outcomes (Study What Questions) |
| Individual worker | Help appreciate benefits of prevention and transformative paradigm through educational process Deliverable: Staff Training | Improved appreciation of blending ameliorative and transformative approaches Deliverable: New practices reflective of transformative paradigm, such as preventive work and increased community input in decision making | Study how individual workers change and embrace new paradigm Deliverable: Model of change process at the individual level | Assess impact of consultation process on individual worker’s practices Deliverable: Evaluation of change at individual level |
| Teams within agency | Assess systematically current practices in light of ameliorative and transformative paradigms Deliverable: Training and evaluation of dominant practices | More balanced approach to wellness that integrates best elements of amelioration and transformation Deliverable: New structures to implement and monitor new integrative approach | Study how teams change and embrace new paradigm Deliverables: Report of change process at team levels | Assess impact of consultation process on team’s practices Deliverables: Evaluation of change at the level of team practices |
| Organizational practice | Evaluate organizational practices in light of transformative and ameliorative paradigms, and promote integration of two modalities Deliverable: Evaluation of organizational practices across agency | Restructuring of programs, policies and practices in line with transformative paradigm Deliverable: A report comparing how new practices compare with old ones and how innovations promote central tenets of transformative paradigm | Study forces enabling and inhibiting change at organizational level Deliverable: Report describing process of organizational change, including internal and external forces enabling and suppressing change | Describe and evaluate organizational change stemming from consultation process Deliverable: Best practice model of organizational change based on qualitative and quantitative data |
| Levels of Change | Consultation Process cont. | Consultation Outcomes cont. | Research Process cont. | Research Outcomes cont. |
| Community wellness | Work with agencies to engage community in process of change, increasing resident participation (voice) and empowerment (choice) and advocating for prevention and promotion Deliverable: Best practice models for enhancing community participation and empowerment | Structures for prevention, participation, and empowerment are put in place Deliverable: Report on best practices for sustainability | Research how agencies engage community in pursuit of wellness and how they sustain efforts at resident involvement Deliverable: Report on strengths and weaknesses of approaches used to increase resident participation | Study organizational structures put in place to ensure sustainability of efforts at prevention and community improvement Deliverable: Framework for sustainable and systemic efforts to involve community in improving social conditions |
| Policy context | Help to establish network of agencies invested in prevention and the transformative paradigm. This network can become a coalition for change at the city, regional, state, and national levels Deliverable: Strategy to enlist United Way and agencies in establishing coalition of human services for prevention and transformation | Meetings with agencies and FRCs participating in project to establish coalition. At a more advanced stage the coalition can grow to agencies not participating directly in project but interested in transformation Deliverable: Facilitation of coalition and network meetings, training of partners in prevention, empowerment and transformation | Understand forces enabling and inhibiting growth of coalition and policy changes in city, regional, state and national levels Deliverable: Report on processes leading to creation of coalition and policy changes at various levels of intervention | Study policy changes that foster sustainability of preventive and transformative paradigm taking place in professional associations, funding bodies, agencies, city, and region Deliverable: Study of policy changes generated through networking, advocacy, education, and intervention at various levels |

Changing Paradigms in Human Services - Project Logic Model (Draft)

Inputs				Activities			Outputs			Outcomes			Impact

# Explanation of collaborative action model

Outer line represents the cycle of the main phases of the intervention.

Inner line connecting circles at the four corners represents the relationships among the four groups of key players

Innermost circle contains the three groups of key factors

The words “sustain and evaluate” pertain to the entire diagram and to the three lines and relationships described above

Basic assumptions of the intervention model include:

- The progression from one phase to the next is not entirely linear. Sometimes we need to go back and do more planning, even if we’re already in the implementation phase. For each phase of the intervention to succeed (4 phases in outer line), we need to pay attention to the contents of each circle in the figure, and to the relationships among them.  For example, we need to ask ourselves how well we’re conveying the need for, and the contents of, a new paradigm in human services. We also need to consider to what extent we’re being participatory, promoting ownership and meaning during the process, and also how involved external actors are in each phase of the project. Each factor within the key factors circle can be translated into a question that can guide the intervention.

- The key factors influence and are influenced by the key players and the relationships among them (illustrated by double headed arrows going from key factors to the relationships among key players

- The roles of key players change during different phases. During the first phase external promoters of change play a large role and external actors or beneficiaries a relatively small role. This can be illustrated graphically by enlarging or reducing the size of the circles of the various players.

- Each circle within the diagram is worthy of a diagram on its own. Within key factors, under principles, we need to understand how power sharing or lack thereof can affect levels of participation and ownership of the process. Within the messages circle, we need to understand how the content of the new, transformative paradigm we’re trying to advance is communicated. We need to know how the form of the delivery interacts with assimilation of the content. Within the structures circle, we need to pay attention to the optimal structures that maximize participation without losing efficacy and accountability.

- The circles are interdependent. Each one satisfies a necessary but insufficient condition for the success of the intervention. A good and clear message about the new paradigm is wasted if there are no good and stable structures to carry out the message. Similarly, good structures cannot foster ownership among workers if they are not participatory.

Implications for evaluation:

- Each circle and the relationships among circles can be subjected to process and outcome evaluations.

- Similarly, each phase needs to be subjected to process evaluations. While we produce and deliver a summative evaluation at the end of the project, process evaluations need to take place as we go along.

- To proceed with the process evaluation, we can take each circle within this overview map of the project and assess how well its factors are contributing to the intervention. For example, we can assess how participatory each phase of the process has been. Similarly, we can evaluate how well the different structures are working. If we have steering committees within each organization, we can periodically ask participants what is their view about the committee’s effectiveness, processes, etc.

Changing Paradigms in Human Services

### Project Structure

Changing Paradigms in Human Services  - Preliminary Plan

| Phase I: Reflection, readiness and visioning August 04 – January 05 | Phase II: Planning and design February – June 05 | Phase III: Implementation July 05-June 07 | Phase IV: Dissemination September 06-June 07 |
| --- | --- | --- | --- |
| Action Tasks | Action Tasks | Action Tasks | Actions Tasks |
| Establish coordinating committee and procedures | Agencies assess concordance between new vision and existing paradigm | Set timelines for implementation of new or reinforcement of existing programs and policies | Update website with materials and lessons gathered so far |
| Establish T-teams and procedures | Using logic and intervention models, identify areas of strength and areas in need of change within agency | Restructure existing jobs and/or introduce new ones | Make presentations to other United Way agencies regionally and nationally |
| Learn about new paradigm | Agencies set up task forces to identify new possibilities for action | Provide training for new jobs or duties | Make available progress reports, papers and presentations |
| Reflect on dominant paradigm within agency | Task forces involve workers in strengthening or inventing new practices | Set up opportunities and structures to assess how new initiatives are evolving | Seek funding to expand project beyond Middle Tennessee |
| Establish participatory process for creating new visions | Formulation of new programs, practices, and policies | Provide support to people in new roles |  |
| Set up website for information and communication |  |  |  |
| Research Tasks | Research Tasks | Research Tasks | Research Tasks |
| Obtain feedback about evaluation tools | Continue to gather process data through observations, etc. | Second wave of data collection for outcome evaluation in Oct 05 | Collect third wave of data around February – March 07 |
| Obtain quantitative baseline data for evaluation | Prepare process feedback summaries as they become available | Continue collection of process data | Code qualitative and quantitative data |
| Conduct interviews | Input data from phase 1 into database | Input of data into databases | Produce final evaluation report on process and outcomes by May 07 |
| Conduct focus group | Meet with agencies to provide formative evaluation input | Produce feedback reports as they become available |  |
| Gather archival information for evaluation |  |  |  |

# Text boxes

Revise existing or create new preventive programs and policies

New or improved prevention programs and policies

Fewer specific personal, interpersonal, and collective problems

Committed staff and organizational leaders

Clients and workers report more appreciation of their strengths

Community members and workers report more voice and choice in work and community

Improved community conditions

New or better opportunities for workers and citizens to experience voice and choice

Increased involvement of services and communities in   improving social conditions

Maximize opportunities to build on worker and client strength

Promote opportunities for workers and citizens to experience participation and empowerment

Enhance or create opportunities for workers and citizens to improve social conditions

Protocols and procedures to build on worker and client strengths

United Way support

Community members with knowledge and experience with services

Improved health and human services

Improved community well-being

External consultants with research and practice expertise

Our intended results

Our planned work

Principles

Principles

Participation

Power sharing

Ownership

Meaning

Structures

Committees

Forums

Workshops

Training

Messages

Content of new paradigm

Form of delivery

Internal actors and/or beneficiaries of change

(Workers in the organization)

External actors and/or beneficiaries of change

(Community members)

External promoters of change

(Vandy team, United Way)

Internal promoters of change

(Organizational leaders)

Phase 3: Implementation

Phase 4:

Dissemination

Phase 1: Reflection, readiness, and visioning

Phase 2: Planning and Design

United Way Team

Vanderbilt Team

Coordinating Committee:

Vanderbilt Team

United Way Team

Reps from all agencies

Monthly meetings

Oasis

Bethlehem

F & CS

UNHS

Martha O’Brian

T-Team

Unit reps

Vandy

UW

Meet to plan and monitor process

T-Team

Unit reps

Vandy

UW

Meet to plan and monitor process

T-Team

Unit reps

Vandy

UW

Meet to plan and monitor process

T-Team

Unit reps

Vandy

UW

Meet to plan and monitor process

T-Team

Unit reps

Vandy

UW

Meet to plan and monitor process

Various Units within Agencies Actualize Plan, Share Information, and Come Together to Foster Common Vision

Coalition of Change Agencies

Changing Paradigms in Human Services Collaborative Action Model